**PASET-RSIF Results: Year III, November 2020**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Results  | Baseline (2018)  | End of project target (2024) | Achieved  | Percentage achievement  |
| Regional Scholarship and Innovation Fund (US $) | 9 | 65 | 20 | 31% |
| General Fund (US $) | 9 | 50 | 20 | 40% |
| Permanent Fund (US $) | 0 | 15 | 0 | 0% |
| PhD Scholars enrolled  | 16 | 96 | 82 | 85% |
| Female PhD Scholars  | 4 | 30 | 30 | 100% |
| Networks between host universities and international partners for PhD training and research collaborations | 0 | 10 | 0 | 0% |
| Number of students and staff trained in cross-cutting courses, entrepreneurship, or research commercialization  | 0 | 120 | 264 | 220% |
| Research papers published by staff members or scholars supported by the project  | 0 | 35 | 17 | 49% |
| Research papers published by female staff members or scholars supported by the project  | 0 | 10 | 3 | 30% |