**PASET-RSIF Results: Year IV, February 2022**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Results | Baseline (2018) | End of project target (2025) | Achieved | Percentage achievement |
| Regional Scholarship and Innovation Fund (US $) | 9 | 50 | 36.7 | 73% |
| General Fund (US $) | 9 | 50 | 36.7 | 73% |
| PhD Scholars enrolled | 16 | 96 | 258 | 269% |
| Female PhD Scholars | 4 | 30 | 90 | 300% |
| Networks between host universities and international partners for PhD training and research collaborations | 0 | 10 | 0 | 0% |
| Number of students and staff trained in cross-cutting courses, entrepreneurship, or research commercialization | 0 | 120 | 570 | 475% |
| Research papers published by staff members or scholars supported by the project | 0 | 35 | 64 | 183% |
| Research papers published by female staff members or scholars supported by the project | 0 | 10 | 17 | 170% |